# PRD — Finishing the HCLS AI Factory

Adam Jones

2026-08-17

Table of Contents

# PRD — Finishing the HCLS AI Factory

Date: 2026-08-17 · Owner: Adam Jones · Companion: FACTORY_COMPLETION_WORKBOOK.docx Status of this document: repo-only. It is not published to hcls-ai-factory.org.

## 1. The problem in one paragraph

The HCLS AI Factory is built but not running. Forty-two capabilities are registered, 8,402 tests pass across all seventeen subjects, the merge gate is green, and the public site is accurate. But on the reference machine two of roughly twenty services are up, there is no .env file at all, the vector database on the expected port belongs to a different stack, and 7 of 17 demonstrations can run. The distance between “the code is real” and “a visitor can watch it work” is the whole of this document.

Nothing here is a rewrite. The gap is bring-up, credentials, gated software, and seeding — in that order.

## 2. Measured starting state (2026-08-17)

Every figure below was produced by running a check, not by reading a doc.

| Dimension | State |
| --- | --- |
| Registry | 42 capabilities — 25 live · 9 verified · 7 planned · 1 gated |
| Tests | 8,402 passing, 0 failing, 17/17 subjects |
| Services responding | 2 (:5000 genomics, :5001 precision-intelligence) |
| .env | absent entirely; 0 of 4 required values set |
| Milvus :19530 | occupied by imaging-milvus-standalone, 12 imaging collections only |
| Demos with prerequisites met | 7 of 17 |
| Per-service venvs | 3 of ~20 supervised services |
| HCLS engine/agent container images | 0 built (149 unrelated images on the box) |
| Compose services declared | 26 |
| Python packages missing from platform venv | 13 of 25 checked (pysam, cyvcf2, rdkit, monai, SimpleITK, e3nn, openai, langgraph, minio, redis, pynvml, plotly, fhir.resources) |
| System binaries missing | 8 of 13 (samtools, bcftools, tabix, bgzip, nextflow, gatk, ffmpeg, pbrun) |
| CUDA | works — torch 2.12.1+cu130, GB10 at sm_121 — but only in core/engines/therapeutic-discovery/venv |
| GPU allocation | fails: 99 GiB of 119 GiB unified memory held by the host page cache |
| Reference data | ClinVar + AlphaMissense present (1.5 GB hcls-ai-factory-core-data/); GRCh38 absent; HG002 FASTQ are 0-byte placeholders |
| Security | HCLS_API_KEY unset — all 12 entrypoints open |
| Governance gates | middleware 11/12 · input gate 1/12 · honesty gate 1/12 |
| CI | green overall, but the subject-suite job is failing under continue-on-error: true |

## 3. What “finished” means

Five acceptance criteria. Each is a command whose output settles it — no judgement calls.

| # | Done when | Command that proves it |
| --- | --- | --- |
| A1 | Every registered live capability answers a health probe | scripts/validate_registry.py --probe (to be added, R11) |
| A2 | All 17 demonstrations run start to finish and write a transcript | run_demo.py --check-all reports 17/17; run_demo.py --all exits 0 |
| A3 | The platform survives a reboot unattended | reboot, wait 5 min, --check-all still 17/17 |
| A4 | A stranger reproduces the quickstart on a clean clone | run_all_tests.py → 17 subjects, 0 failed; run_demo.py E8 → PASS |
| A5 | Nothing on the site claims more than the box delivers | mkdocs build --strict green and every live badge backed by A1 |

The honesty rule stands throughout: a capability is promoted only after it answers a probe; a demo is labelled LIVE only after it has run on real input. If a phase cannot reach its criterion, the registry status changes — not the criterion.

## 4. Requirements

Priority: P0 blocks everything · P1 blocks a phase · P2 quality.

### 4.1 Foundation (no accounts needed)

| # | Requirement | Pri | Done when |
| --- | --- | --- | --- |
| R1 | .env exists from .env.example with all four required values | P0 | docker compose config resolves with no warnings |
| R2 | HCLS_API_KEY set; auth verified fail-closed | P0 | 401 without key, 401 wrong key, 200/405 with key |
| R3 | 13 missing Python packages installed into the platform venv | P1 | import check passes for all 25 |
| R4 | 6 free system binaries installed (samtools bcftools tabix/bgzip nextflow gatk ffmpeg) | P1 | each on PATH, --version responds |
| R5 | Page-cache drop added to bring-up so CUDA can allocate | P0 | torch.cuda.mem_get_info() returns without error |
| R6 | A dedicated Milvus for HCLS that does not collide with the imaging stack | P0 | HCLS connects and lists its own collections |

### 4.2 Bring-up

| # | Requirement | Pri | Done when |
| --- | --- | --- | --- |
| R7 | One runtime model chosen — compose or host processes, not both | P0 | decision recorded in this PRD §7 |
| R8 | All 26 compose services build and start | P1 | docker compose ps shows all healthy |
| R9 | Agent corpora seeded for all eight agents | P0 | each agent’s collections exist and return hits |
| R10 | Services restart automatically after reboot | P1 | A3 passes |
| R11 | validate_registry.py --probe added — fails CI on a live capability that does not answer | P1 | flipping a service off turns CI red |

### 4.3 Gated software

| # | Requirement | Pri | Done when |
| --- | --- | --- | --- |
| R12 | NGC account + docker login nvcr.io succeeds | P0 for this phase | Login Succeeded |
| R13 | CUDA PyTorch behind the platform venv and every GPU service | P1 | cuda.is_available() true from the platform interpreter |
| R14 | Parabricks pulled; FASTQ→VCF runs on real HG002 | P1 | VCF written, Ts/Tv ≈ 2.0 |
| R15 | MolMIM + DiffDock NIMs deployed or the arch answer recorded and demos relabelled BURST | P1 | either containers healthy, or §7 decision + relabel |
| R16 | Real HG002 FASTQ downloaded (~200 GB) and GRCh38 obtained | P1 | files non-zero, index built |

### 4.4 Demonstrations

| # | Requirement | Pri | Done when |
| --- | --- | --- | --- |
| R17 | 17/17 demos have prerequisites met | P0 | --check-all reports 17/17 |
| R18 | Every demo writes a diffable transcript | P1 | demo/transcripts/*.txt for all 17 |
| R19 | Each demo’s label matches what actually ran | P0 | LIVE only where the service answered |
| R20 | Demo catalogue counts regenerated from the runner, not hand-written | P2 | catalogue figures come from --check-all |

### 4.5 Quality debt

| # | Requirement | Pri | Done when |
| --- | --- | --- | --- |
| R21 | Subject-suite CI job made blocking and green | P1 | continue-on-error removed, run green |
| R22 | require_valid_input() / honesty_flags() called by handlers, not just available | P1 | coverage 12/12 on the governance page |
| R23 | 12 stdlib-shadowing modules renamed (src/collections.py → vector_collections.py) | P2 | bare pytest works without the harness |
| R24 | structural-biology aggregator on :8581, or the engine stays planned | P2 | probe answers, or status unchanged |
| R25 | Test-depth floor agreed for clinical-output subjects | P2 | recorded; range is currently 4 → 1,966 |

## 5. Phases

Each phase has an exit gate. Do not start the next phase until the gate passes — the reason is in §8, and it is the difference between debugging one thing and debugging four.

Phase 0  Foundation        R1-R6        no accounts        ~1 day
   │     gate: .env resolves, API key fails closed, CUDA allocates, HCLS Milvus up
   ▼
Phase 1  Bring-up          R7-R11       free               ~2-4 days
   │     gate: all services healthy, corpora seeded, 13+ demos ready, survives reboot
   ▼
Phase 2  Free accounts     B-tier       HuggingFace, NCBI, Anthropic   ~1 day
   │     gate: BGE embeds, Claude answers, agents return cited output
   ▼
Phase 3  Gated software    R12-R16      NGC entitlement    unknown — the long pole
   │     gate: Parabricks produces a real VCF; NIM arch question answered
   ▼
Phase 4  Demonstrations    R17-R20      free               ~3-5 days
   │     gate: 17/17 run, transcripts recorded, labels honest
   ▼
Phase 5  Quality debt      R21-R25      free               ongoing
         gate: CI blocking and green; governance coverage stated as a number

Phases 0, 1, 2, 4 and 5 need no gated software. That is roughly 80% of the remaining work and it is all unblocked today. Phase 3 is the only part waiting on someone else.

## 6. Non-goals

Stating these prevents scope creep into work that does not move A1–A5.

- Not a multi-node or Kubernetes deployment. One box plus elastic burst is the thesis.

- Not clinical validation, regulatory submission, or a medical-device claim.

- Not new capabilities. Forty-two is enough; finish them.

- Not raising test counts for their own sake. Depth where output is clinical (R25), not everywhere.

- Not re-architecting the engine/agent split, the registry, or the port convention.

- Not publishing the internal build docs to the public site. They stay in the repo.

## 7. Open decisions — you must answer these

These are yours, not mine. Each blocks a requirement, and guessing wrong costs days.

| # | Decision | Blocks | Why it matters |
| --- | --- | --- | --- |
| D1 | Compose or host processes? The compose file calls itself the portable target; health-monitor.sh runs the live system. Both are half-maintained. | R7, R8, R10 | Two runtime models means every service is configured twice and drifts. Pick one; delete or clearly demote the other. |
| D2 | Are MolMIM and DiffDock x86-only? | R15 | If yes, they can never run locally, the flagship drug-discovery demo is permanently BURST, and every script must say “elastic burst”. Determine before building demos around them. |
| D3 | Which Milvus does HCLS use? :19530 is the imaging stack’s. Share it (namespaced collections) or stand up a second on another port. | R6, R9 | Sharing risks one stack’s reset wiping the other’s corpora. |
| D4 | AlphaMissense is CC BY-NC-SA — non-commercial. It is the most-referenced external artefact in the codebase (455 refs) and the platform is Apache-2.0 with “commercial use welcome”. | R16, site copy | A licence conflict at the centre of the value proposition. Either scope the claim, isolate the dependency, or accept and document. |
| D5 | Is 200 GB of HG002 FASTQ worth the disk? The placeholders are 0 bytes today. | R14, R16 | A downsampled chromosome subset may prove the pipeline at a fraction of the cost. |
| D6 | Does the video build tree stay local-only? tmp/ is gitignored — every script and cached take lives on one disk. | — | Losing it loses the ability to edit your primary assets. |

## 8. Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| NGC entitlement never arrives | medium | Phase 3 blocked | Phases 0–2, 4–5 are independent. Relabel affected demos REPRESENTATIVE and ship. |
| MolMIM/DiffDock are x86-only | likely | flagship demo cannot run locally | Answer D2 early; write the burst path into the narration now, not later. |
| Page cache re-fills and CUDA fails again | high | intermittent GPU failure | R5 makes the drop part of bring-up, not a manual step. |
| Shared Milvus wiped by the other stack | medium | all agent corpora lost | D3; back up collections before any reset. |
| Bringing up four things at once | high | cannot tell which failed | The phase gates exist for exactly this. |
| Registry drifts from reality once services run | medium | the honesty claim breaks | R11 makes CI enforce it. |
| AlphaMissense licence surfaces publicly first | low | credibility | D4 now, on your terms. |

## 9. What this buys

When A1–A5 pass, the site’s central claim — fork it and run it yourself — becomes literally true for a stranger, the 17 demonstrations become watchable rather than described, and the maturity matrix becomes a live readout rather than a periodic audit. That is the difference between a project that is impressive to read and one that is impressive to use, which is the gap the current site cannot close on its own.

Work the Workbook in order. It carries the exact commands, the verification after each step, and the traps that have already cost time on this machine.